## Sheet1
Task Name | Estimate time( hour) | Take by | Actual Time | Status | Date Doing | Complete Process
Design GUI for Website | 18 | Võ Huỳnh Đức Minh | 24 | Done | 28/3/2020 | 24
[Front-end]Login Component | 2 | Võ Huỳnh Đức Minh | 2 | Done | 2020-01-04 | 2
[Front-end]Logout Component | 2 | Võ Huỳnh Đức Minh | 2 | Done | 2020-01-04 | 2
[Front-end]Register Component | 2 | Võ Huỳnh Đức Minh | 6 | Done | 2020-01-04 | 2
[Front-end]View Product Component | 4 | Võ Huỳnh Đức Minh | 4 | Done | 2020-02-04 | 4
[Front-end]View Product Detail Component | 2 | Võ Huỳnh Đức Minh | 2 | Done | 2020-02-04 | 2
[Front-end]Shopping Cart Component | 10 | Võ Huỳnh Đức Minh | 16 | Done | 2020-03-04 | 10
[Front-end]Validation Form | 6 | Võ Huỳnh Đức Minh | 8 | Done | 30/3/2020 | 6
[Front-end]CRUD Product Component | 6 | Võ Huỳnh Đức Minh | 10 | Done | 2020-01-04 | 6
[Front-end]CRUD User Component | 6 | Võ Huỳnh Đức Minh | 10 | Done | 2020-02-04 | 6
Total | 58 |  | 144.8% |  | Done task: | 110.3%
Requirement analyze | 2 | Nguyễn Công Bảo | 2 | Done | 25/3/2020 | 2
[Report 1] Proposed Solution | 2 | Nguyễn Công Bảo | 2 | Done | 26/3/2020 | 2
[Report 1] Functional Requirement | 2 | Nguyễn Công Bảo | 2 | Done | 26/3/2020 | 2
[Report 1] Roles and Responsibility | 2 | Nguyễn Công Bảo | 2 | Done | 26/3/2020 | 2
Learning for Restful API | 10 | Nguyễn Công Bảo | 48 | Done | 30/3/2020 | 10
[Front-end]Login Component | 2 | Nguyễn Công Bảo | 2 | Done | 2020-01-04 | 2
[Front-end]Register Component | 2 | Nguyễn Công Bảo | 2 | Done | 2020-01-04 | 2
[Front-end]View Product Component | 2 | Nguyễn Công Bảo | 2 | Done | 2020-01-04 | 2
[Front-end]View Product Detail Component | 2 | Nguyễn Công Bảo | 2 | Done | 2020-01-04 | 2
[Front-end]Shopping Cart Component | 2 | Nguyễn Công Bảo | 2 | Done | 2020-01-04 | 2
[Front-end]CRUD Product Component | 8 | Nguyễn Công Bảo | 8 | Done | 2020-01-04 | 8
[Front-end]CRUD User Component | 8 | Nguyễn Công Bảo | 8 | Done | 2020-01-04 | 8
Draw User-case Diagram | 1 | Nguyễn Công Bảo | 2 | Done | 2020-03-04 | 2
Draw Sequence Diagram | 1 | Nguyễn Công Bảo | 1 | Done | 2020-03-04 | 2
Draw ClassDiagram | 1 | Nguyễn Công Bảo | 2 | Done | 2020-03-04 | 2
Design Database | 5 | Nguyễn Công Bảo | 10 | Done | 27/3/2020 | 10
Total | 52 |  | 188.5% |  | Done task: | 115.4%